## Timeplanning
Tasks | Week | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Saxion | bar: 9; 18
Plan of action | bar: 7 to 9; 18; 28
Research | bar: 9; 18; 28
Background | bar: 9 to 11; 18; 28
Market (desk- & fieldresearch) | bar: 9 to 15; 18; 28
Product | bar: 9 to 15; 18; 28
Implementation | bar: 9; 18; 28
Product designs | bar: 9; 16; 18 to 22; 28
Business plan | bar: 9; 18 to 24; 28
Conclusion and recommendations | bar: 9; 18; 24 to 26; 28
AAU
Implementation of server | bar: 7 to 9
Make a requirement specification | bar: 7 to 11; 22
Research | bar: 9 to 16; 18 to 22
Improving the honeypot | bar: 10 to 16; 18 to 20; 22
GUI | bar: 10 to 16; 18 to 20; 22
UTP | bar: 22
Research | bar: 22
Containment zone | bar: 7 to 9; 16; 18 to 22
Network Analyses | bar: 10 to 15; 22
AGU | bar: 22
Research | bar: 7 to 16; 18 to 22
Network Analyses | bar: 10 to 15; 22
Machine Learning | bar: 18 to 22
Optimizing python script | bar: 7 to 10; 22
Important Meetings | bar: 22
Documentation and acces to honeypot | bar: 10
Danish and Anna on research (honeypot) | [23 empty] | Legend: | bar: 10
Plan of action (draft) bussines | [24 empty] | Vacation | bar: 9
Grades | [24 empty] | Time to work | bar: 10; 16; 20
Time to work
Deadline
Milestones
Trip